## Instructions
Project Data-centric Maturity Assessment Tool
Introduction
This spreadsheet provides a tool to assess the data-centric maturity of construction projects. It is recommended that the project’s data-centric committee conduct this assessment. The project maturity matrix located in the “Maturity Matrix” tab has 24 assessing elements organized in 6 categories. For each element, there are 6 progression levels and a weight factor. All the cells are locked except three columns, including “Weight Factor,” “Achieved Level,” and “Planned Level.”
Instructions
1- It’s recommended to specify the weight factor for each element first. The weight factor ranges between 0 to 1 with 0.1 increments. If an element doesn’t apply to your project, you can choose 0 in the “Weight Factor” dropdown menu.
2- After choosing the weight factors, you need to choose the “Achieved Level” and “Planned Level” for each element. This can be done by choosing a number from 0 to 5 in the “Achieved Level” and “Planned Level” columns.
3- After you go through all of the 24 elements, you can see your total scores in row 43. In addition, the “Summary” Tab shows a summary of the categories, their elements, and their scores.
Assessor Data
Name of the project | ABC project
Name of the data-centric committee memebers or person(s) who filled this maturity matrix | Name, Name, Name
Date | MM/DD/YYYY
Project delivery type | Design-Bid-Build
Project duration | X years
Project value | 50000000
Project number | 111111
Comment | To be reviewed by Name
Copyright © 2021 Construction Industry Institute™ The University of Texas at Austin CII members may reproduce and distribute this work internally in any medium at no cost to internal recipients. CII members are permitted to revise and adapt this work for the internal use provided an informational copy is furnished to CII. Available to non-members by purchase; however, no copies may be made or distributed, and no modifications may be made, without prior written permission from CII. Contact CII at https://www.construction-institute.org/catalog.htm to purchase copies. Volume discounts may be available. All CII members, current students, and faculty at a college or university are eligible to purchase CII products at member prices. Faculty and students at a college or university may reproduce and distribute this work without modification for educational use.

## Maturity Matrix
|  | Project Data-centric Maturity Assessment Tool | [6 empty] | Project's name |  |  |  | ABC Project
[9 empty] | Planning Committee Member(s) |  |  |  | Name, Name
[9 empty] | Current Date |  |  |  | MM/DD/YYYY
[9 empty] | Project number/name |  |  |  | 111111111
|  |  | Level of Maturity | [9 empty] | Comment | Both 0 | Both 1 | Both 2 | Both 3 | Both 4 | Both 5
No. | Planning Element | Description | 0 Non-Existent | 1 Initial | 2 Managed | 3 Defined | 4 Quantitatively Managed | 5 Optimizing | Planned Level | Achieved Level | Total Possible | Weight Factor
|  | The mission, vision, goals, and objectives, management support, data-centric champions, and planning committee and financial support. | Category 1 – Strategy
P1 | Project Goals and Objectives | Develop data-centric project goals and objectives for the execution of the project | No data-centric project goals or objectives defined | Basic data-centric project goals are established | Established basic data-centric objectives | Clear data-centric SMART goals that are specific, measurable, and attainable to manage projects and assets | Clear data-centric SMART goals along with the process to capture lessons learned to advance future projects | Robust SMART data-centric project goals and objectives that are regularly revisited and maintained | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P2 | Planning Committee | Create a data-centric planning committee that is responsible for developing the project data-centric plan | No data-centric planning committee established | Small Ad-hoc committee with only those interested in data-centric | The data-centric committee is formalized but not inclusive of all stakeholders | Multi-disciplinary data-centric planning committee established with members from all data-centric stakeholders | The planning committee engages regularly and proactively to plan for meeting project needs and solve problems | Data-centric planning decisions are integrated with organizational advancement and support innovative data-centric adoption | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P3 | Management Support | Obtain management level support for the data-centric planning process | No management support | Permission to pilot, but no resources made available | Limited support for continuing efforts with a limited budget | Full support for data-centric implementation with some resource commitment | Full support for data-centric implementation with appropriate resource commitment | Full support of continuing efforts with a well-defined budget | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P4 | Financial Support | Commit financial resources for a data-centric approach at the project-level | No financial support | Pilot funding to explore | Partial funding incorporated in the project budget | Funded for the current minimum required project goals | Fully funded for the current data-centric project goals | Funding for support of innovative data-centric adoption | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P5 | Owner Commitment | Obtain owner commitment to implement a data-centric approach on the project | No motivation from the owner | The owner has limited support for the data-centric approaches depending on the initial cost | The owner supports data-centric tools and approaches on a case by case | The owner is invested in adoption data-centric approaches to support capital facility delivery | The owner has integrated tools to be able to leverage the data-centric approach | The owner puts effort into defining data-centric requirements; establishes a system to receive final data which is engrained in the processes | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P6 | Information Security | Secure information to the level necessary while still supporting collaboration | No defined security approach for information | Basic non-disclosure agreement in place | A documented approach that is followed | Dedicated team to look into security | Regular information security check on the data files and alerts on irregular access | Clear definition of levels of security, a system in place to test the security | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P7 | Information Quality Management | Perform a process to ensure data quality, and then test and check | No defined process | Check that deliverables are received but not file content checking | Manual Check | Automated quality control for the right type of data | Fully auto-check quality control, all data checked | Artificial intelligence or other advanced checking tools for quality control and checking the validity of data | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P8 | Change Management | Develop strategy and processes for adopting new technologies and practices to support a data-centric approach on the project level | No change management strategy | Ad hoc strategies including updates on the software used on the project | Established a basic change management strategy for the data-centric approach | Change management processes are part of the contract | Data-centric committee supervise the change management processes to some extent | Data-centric planning committee conduct regular reviews on the current strategies and actively seeks new technologies on the market to improve productivity | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
[7 empty] | Totals |  | 0 | 0 | 40 | N/A
|  | Personnel assigned to a project who work collectively to achieve shared project goal(s) | Category 2 – People | [10 empty] | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
P9 | Information Management Champion(s) | Identify a project IM Champion that is technically skilled and motivated to guide a project to plan and implement their data-centric processes | No champion, passive data management | Grassroots champion, not formally recognized | Part-time champion or project manager | Clearly defined champion working under the project manager | Champion is a defined role within the project team, with clear project authority to implement data-centric processes | Champion answers directly to project leadership/director; is a full-time role on the project, has budget and resources for implementation | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P10 | Roles and Responsibilities | Define clear roles and responsibilities for data-centric execution of the project | No roles and responsibilities defined | Data-centric approaches are the responsibility of the champion | Data-centric approaches are the responsibility of all project team groups | Data-centric responsibilities lie within each team involved in the project | Data-centric approaches are defined for each person and team | Data-centric approach responsibilities are regularly reviewed to ensure they are properly distributed | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P11 | Training | Education and training to support upskilling, onboarding, and employee development | No capability to educate employees | Basic capability to educate employees to pockets of knowledge and skills related to data-centric approaches | An organized network of experts / SMEs to support education and training | Standardization of value-adding elements for education and training modules for delivery; integrated into onboarding and promotion or role transitions | Education and training for digitalization have been integrated into regular programs | Continuous improvement and evolution of new competencies or skills identified in conjunction with emerging best practices | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
[7 empty] | Totals |  | 0 | 0 | 15 | N/A
|  | The procurement and contracting approaches support the implementation of a data-centric approach | Category 3 – Procurement and Contracts | [10 empty] | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
P12 | Procurement and Contract Documents | Develop contractual documents and a procurement strategy that supports a data-centric approach | No data-centric goal is mentioned in the procurement documents | Basic support of data-centric approaches in the procurement/contract documents | Some data-centric goals are mentioned in the procurement/contract documents | Procurement/contract documents support data-centric approaches but not standard roles and responsibilities, governance information, typical planning, and implementation requirements | Procurement/contract documents support and facilitate data-centric approaches, standards, procedures, and responsibilities | Procurement documents support, facilitate and make it a requirement to adopt data-centric approaches | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P13 | Team Selection Criteria | Select team members through the consideration of the data-centric capabilities of potential team members | Data-centric capabilities not considered in team selection | Ad hoc consideration of data-centric capabilities in team selection | Basic criteria for service provider selection process and qualification based on data-centric capabilities and usage on a project basis | Clearly defined selection criteria are defined for typical service provider capabilities and are used to narrow qualified firms on most projects. | Data-centric selection criteria are well defined and consistently used on projects; service providers are reviewed to track conformance with proposed qualifications. | Data-centric selection criteria are coupled with other factors to select best-in-class service providers and continuously improve criteria to improve project adoption and outcomes. | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P14 | Asset Information Requirement (AIR) | Define clear AIR by the owner to include interim and final information model deliverables | No asset information requirements | Vague language for handover requirement in the contract; the owner will specify during the construction phase gradually | Have requirements, but not clearly documented (other stakeholders define) | Clear sets of handover requirement in the contract, but the requirements are not conveyed as digital templates | Complete set of contract handover requirements and digital data files listing all the required asset for handover | A defined set of requirements that are maintained through a process that is enforced and measured | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
[7 empty] | Totals |  | 0 | 0 | 15 | N/A
|  | A strategy to develop a data-centric process to support information creation, sharing, and reuse. | Category 4 – Process | [10 empty] | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
P15 | Data Governance Plan | Define a set of strategies, goals, and plans that outline the collaboration processes between project parties | No plan is defined | A basic plan from previous projects is used | A basic plan for the project is defined | A specific and clear plan is developed and followed by the project | A clear, specific plan is designed and regularly reviewed by the project team | A data-centric execution plan is designed, well defined, reviewed, and supported by all project teams | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P16 | Performance Management | Define a set of procedures and plans to measure the performance of data-centric approaches | No plan is defined | Ad hoc performance measurement | Some performance measurement across the teams and different disciplines | Performance measurement is defined as part of the project strategy and regularly measured | Fully defined performance management that is measured regularly and the feedbacks are provided to the teams | Fully automated performance measurement that is regularly updated, misread, and capable of providing feedback to the teams | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P17 | Common Data Environment (CDE) | Develop a single accessible to all source of information for the project to collect, manage and disseminate all relevant approved project documents for multi-disciplinary teams in a managed process | No Common Data Environment | Ad hoc storage of files but not central structure | Central storage location but no standardization of content organization | Central storage location with common naming conventions | Central storage location with defined conventions and processes for updating information | Accessible data environment with clearly defined storage approach, readily accessible by everyone who needs it, and one source of truth | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P18 | Data-Centric Standards and Workflows | Develop project standards for data-centric processes, naming conventions, file exports, level of details, etc. | No standards or a few ad hoc documents | Draft standards and policies are under development and piloted on project(s) | Standards include naming, process, and templates | Standard includes naming, templates, automated alerts, export formats, size of the files, and upload recurrence | Established quality assurance process and metrics to document conformance to standards and policies | Standards are continuously updated based upon conformance to the metrics and new technologies | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
[7 empty] | Totals |  | 0 | 0 | 20 | N/A
|  | Obtain the needed hardware, software, and physical spaces to support the implementation | Category 5 – Infrastructure | [10 empty] | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
P19 | Software | Use software applications to implement the desired data-centric use cases | No data-centric Software | Software capable of accepting data-centric data | Basic data-centric Software Systems | Advanced data-centric software systems | All software systems available to all personnel | Program established for continuous updating of data-centric software systems | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P20 | Hardware | Obtain physical interconnections and hardware devices required to store and execute data-centric software solutions as needed within all project team members | No hardware capable of running data-centric software | Ad hoc outfitting of hardware so some team members have access | Certain personnel have hardware based upon their role or title | Standard (minimum) hardware requirements defined for all team members to meet their needs for accessing data-centric software solutions | All project hardware meets minimum spec for accessing data-centric software, with process for requesting upgrades | Program in place for continuous updating of hardware and systems to support access to data-centric software solutions for all project team members | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P21 | Physical Spaces | Use physical spaces to support the collaborative implementation of the data-centric uses, e.g., a technology-enabled meeting space for reviews for project teams | No dedicated data-centric space | Single workstation for viewing data-centric data | Small workspace for collaborating with a screen large enough for multiple viewers | Interactive workspaces to support data-centric collaboration on a large screen | Multiple collaborative workspaces within a regular workspace | Program established for continuous updating of data-centric spaces | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
[7 empty] | Totals |  | 0 | 0 | 15 | N/A
|  | Identify and implement data-centric use cases throughout the delivery and asset management of the facility | Category 6 – Data Use Cases | [10 empty] | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
P22 | Core Project Delivery Uses | Core project delivery data-centric use cases include BUT NOT LIMITED TO capture existing conditions, author design model, analyze engineering performance, coordinate design model(s), and review design model(s) | No use of core project delivery use cases. | Ad hoc implementation of a subset of core project delivery use cases | Planned, limited implementation of a subset of core project delivery use cases | All core project delivery use cases are implemented | All core project delivery use cases are implemented including tracking of data sharing | All core project delivery use cases are fully implemented with tracking of data sharing and a continuous improvement process | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P23 | Asset Information Handover | Asset information requirements are defined and deliverables are compiled throughout the project | No digital asset information transfer to the owner (paper) | Handover information is primarily in digital documents | Handover information includes digital documents and data files of models without owner requirements | Handover of digital documents and model data files delivered in requested format, structure, and appropriate conventions | Handover of model data files, as requested, support asset management use, including basic quality control checking of data | Advanced asset information requirements are met through model data with process for quality assurance checking of handover files | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
P24 | Advanced Project Delivery Uses | Advanced project delivery data-centric use cases include BUT NOT LIMITED TO quantities and cost estimating creation, author 4D model, layout construction work, and automate equipment guidance | No use of advanced project delivery use cases for a data-centric approach. | Basic capability of using the advanced project delivery use cases through design and construction but not real implementation | Basic capability and implementation of advanced project delivery use cases through design and construction | An extensive capability of using advanced project delivery use cases through design and construction but a basic implementation | Extensive capability and implementation of advanced project delivery use cases through design and construction | Advanced project delivery use cases are extensively implemented with tracking of data sharing and a continuous improvement process | 0 | 0 | 5 | 1 |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | 0
[7 empty] | Totals |  | 0 | 0 | 15 | N/A
Note: This reflects maturity in all sections. While the project could score high, there could be some key areas not implemented that could hinder the project data-centric implementation. | [5 empty] | Total for All Categories |  |  | 0 | 0 | 120 | N/A |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE

## Summary
Data-centric Maturity Assessment Summary
Date Filled: | MM/DD/YYYY
Project Number/Name: | ABC Project
Data-centric Planning Elements | Planned Level | Achieved Level | Total Possible
Category 1 - Strategy
Project Goals and Objectives | 0 | 0 | 5
Planning Committee | 0 | 0 | 5
Management Support | 0 | 0 | 5
Financial Support | 0 | 0 | 5
Owner Commitment | 0 | 0 | 5
Information Security | 0 | 0 | 5
Information Quality Management | 0 | 0 | 5
Change Management | 0 | 0 | 5
Totals | 0 | 0 | 40
Category 2 - People
Information Management Champion(s) | 0 | 0 | 5
Roles and Responsibilities | 0 | 0 | 5
Training | 0 | 0 | 5
Totals | 0 | 0 | 15
Category 3 - Procurement and Contracts
Procurement and Contract Documents | 0 | 0 | 5
Team Selection Criteria | 0 | 0 | 5
Asset Information Requirement (AIR) | 0 | 0 | 5
Totals | 0 | 0 | 15
Category 4 - Process
Data Governance Plan | 0 | 0 | 5
Performance Management | 0 | 0 | 5
Common Data Environment (CDE) | 0 | 0 | 5
Data-Centric Standards and Workflows | 0 | 0 | 5
Totals | 0 | 0 | 20
Category 5 - Infrastructure
Software | 0 | 0 | 5
Hardware | 0 | 0 | 5
Physical Spaces | 0 | 0 | 5
Totals | 0 | 0 | 15
Category 6 - Data Use Cases
Core Project Delivery Uses | 0 | 0 | 5
Asset Information Handover | 0 | 0 | 5
Advanced Project Delivery Uses | 0 | 0 | 5
Totals | 0 | 0 | 15
Totals of all categories | 0 | 0 | 120
| Planned % | Achieved %
Strategy | 0 | 0
People | 0 | 0
Procurement and Contracts | 0 | 0
Process | 0 | 0
Infrastructure | 0 | 0
Data-Use Cases | 0 | 0